## How to use
BOTIn — POC to production release, step by step
80 steps in 9 phases. Sequenced so that each one can be understood and agreed before it is implemented.
HOW WE WORK THROUGH IT
1. Take the next step in order. Phases are sequential; steps inside a phase mostly are not.
2. Steps marked DISCUSS FIRST = Y are design decisions. We agree the approach before any code changes. 49 of the 80 are.
3. Steps marked N are mechanical. I propose the change, you approve, I make it.
4. No code changes without your approval, on any step.
5. Set Status on the Steps tab; the Summary tab is formulas over it and updates itself.
THE SHAPE OF THE PLAN, AND WHY
Phase 0 settles what nobody can compute — the decisions, and the five data answers two read-only probes return.
Phases 1 and 2 are independent of every open decision: the service has to be deployable and the reads have to be correct whatever Phase 1 turns out to contain. They can start immediately.
Phase 3 takes ONE concern all the way to production quality, to prove the Definition of Done is achievable. Recharge, because it is the only concern whose money path is complete — AUTO_CREDIT_WALLET is the single registered action today.
Phases 4 and 5 are the things a service that moves money without a human needs before it is allowed to.
Phase 6 repeats the Phase 3 shape across the remaining concerns. Vertical slices, one concern at a time — a concern that reads, decides, acts and is observable is shippable; a layer is not.
Phase 7 is the front door NFR-01 demands, and it is the long pole: dialer, CTI, agent tooling, audio-note L1, order dropdown. Mostly other teams. Start tracking it early even though it lands late.
Phase 8 is shadow mode, then the go list, then go/no-go.
WHAT THIS PLAN ASSUMES, AND WHERE IT COULD BE WRONG
It assumes Recharge is the right first slice. If Product decides Phase 1 ships Tier 0/1 only, the first slice becomes Forget MPIN and Phase 3 gets cheaper and proves less.
It assumes the taxonomy is settled in step 9. Until it is, Product Issues and Violations — 18,087 monthly cases between them — have no agreed home.
Phase 7 is sized by other teams, not by this codebase. No amount of work here shortens it.

## Steps
# | Phase | Step | What changes in the implementation | Why it matters | Depends on | Discuss first | Status | Notes
1 | 0 — Settle (no production code) | Run tools/uat-probe-2.sql | Nothing. Read-only SQL. | Returns the real names of arrived_at300_m and order_type, the paise-vs-rupees answer, the PayU link column (N3) and cs_address (Q6). | — | N | Not started
2 | 0 — Settle (no production code) | Run tools/uat-probe-3.sql | Nothing. Read-only SQL. | Returns the order_status_code values for NR / CR / by-agent (N2). NR auto-credits where CR denies, so a wrong mapping pays the wrong partners. | — | N | Not started
3 | 0 — Settle (no production code) | Record every probe answer | docs/SIGNAL-REGISTER.md, docs/DECISIONS.md | An answer that lives only in a chat is an answer that gets re-derived wrongly later. | 1, 2 | N | Not started
4 | 0 — Settle (no production code) | Take the 8 reconciliation decisions to Product | docs/DECISIONS.md | 23% of volume is in CONFLICT between the PRD and the concern sheet and 35% is in the catalogue but absent from the PRD. Building either version first is a coin flip. | — | Y | Not started
5 | 0 — Settle (no production code) | Settle the headline number: 86% or 61.5% | docs/DECISIONS.md | Both are forecasts of the same quantity and they differ by a quarter of all volume. Staffing, the agent-connect target and every phase gate are sized off it. | 4 | Y | Not started
6 | 0 — Settle (no production code) | Confirm the Phase 1 concern cut | docs/DECISIONS.md | PRD Phase 1 is Tier 0/1 only. Of what is built, only FORGET_MPIN qualifies; Transport and Recharge are Phase 2. | 4, 5 | Y | Not started
7 | 0 — Settle (no production code) | Confirm the Agent-2 outbound SLA (NFR-03) | Nothing yet; sets the alert threshold later. | Unspecified in the PRD. Decides whether the agent queue needs priority handling. | — | Y | Not started
8 | 0 — Settle (no production code) | Settle the reversible window (NFR-07) | Shapes the ticket_action schema in step 14. | Duration, who may reverse, and whether the partner sees the money. Settle BEFORE the schema port so the table is created once with the states it needs. | — | Y | Not started
9 | 0 — Settle (no production code) | Freeze the concern taxonomy and write the catalogue migration | New Flyway migration over concern_catalogue | The catalogue is the system's configuration. If it describes the wrong world, that is one migration now or a surprise per concern later. | 4 | Y | Not started
10 | 1 — Make it deployable (new service) | Create the service repository properly | Repo layout, branch protection, PR review, versioning | Today it is one commit named 'initial setup'. Nothing downstream is safe without history and review. | — | N | Not started
11 | 1 — Make it deployable (new service) | Dockerfile matching the platform | New Dockerfile | empapi's pattern: ym-base-images ECR builder, temurin-17-jre runtime, Elastic APM agent, ports 8080/9090. | 10 | N | Not started
12 | 1 — Make it deployable (new service) | Per-environment config, the platform's way | src/main/config/{dev,uat,pre-prod,prod}/application.properties + Maven profiles | empapi selects config by Maven profile, not by Spring profile files in resources. Match it. | 10 | N | Not started
13 | 1 — Make it deployable (new service) | Secrets from AWS Secrets Manager | spring.config.import=aws-secretsmanager:<env>/botin | Retires env/botin-uat.env for every deployed environment. Secrets are already solved here; do not invent a second mechanism. | 12 | Y | Not started
14 | 1 — Make it deployable (new service) | Port the schema to MySQL | db/migration/V1 rewritten | escalation_context is five VARCHAR(4000) columns — about 80,640 bytes under utf8mb4, over MySQL's 65,535-byte row limit. The table will not create. Those become TEXT. | 8 | Y | Not started
15 | 1 — Make it deployable (new service) | Decide and apply the UUID representation | V1 + entity mappings | MySQL has no UUID type. CHAR(36) is readable in a SQL client; BINARY(16) is not. Every runbook and every 'why did this partner get paid' query starts with pasting an id. | 14 | Y | Not started
16 | 1 — Make it deployable (new service) | Timestamps and booleans | V1 | TIMESTAMP WITH TIME ZONE has no MySQL equivalent: DATETIME(6) with hibernate.jdbc.time_zone=UTC carrying the contract. BOOLEAN becomes TINYINT(1). | 14 | N | Not started
17 | 1 — Make it deployable (new service) | Re-seed the catalogue for MySQL | db/migration/V2 (and the taxonomy migration from step 9) | Seed data and the frozen taxonomy land together, once. | 14, 9 | N | Not started
18 | 1 — Make it deployable (new service) | Flowable on MySQL | config/FlowableConfig.java, engine properties | Its DDL, optimistic locking, id generator and history tables are engine-specific. | 14 | N | Not started
19 | 1 — Make it deployable (new service) | Testcontainers MySQL for migration and repository tests | src/test, pom.xml | H2 standing in for MySQL would not have caught the row-size limit above — exactly the class of thing that matters. Keep H2 for the rest. | 14 | Y | Not started
20 | 1 — Make it deployable (new service) | Re-prove money safety on MySQL | No new code; the existing tests run against MySQL | REQUIRES_NEW isolation, commit-before-call ordering and the duplicate-credit guard were one of the two POC stop conditions, proved on one engine. | 19 | Y | Not started
21 | 1 — Make it deployable (new service) | Provision the database per environment | Infra; Flyway runs on deploy | — | 12 | N | Not started
22 | 1 — Make it deployable (new service) | Point source reads at the read replica | config/DataSourceConfig.java | empapi already separates prodsqlwr from prodsqlro. The SELECT-only GRANT stays as well: the grant makes writing impossible, the replica makes reaching the primary impossible. | 21 | N | Not started
23 | 1 — Make it deployable (new service) | CI pipeline | Build, full test suite, tools/preflight.py, image push to ECR | preflight catches the JVM-free inconsistencies before a compiler ever runs. | 10, 11 | N | Not started
24 | 1 — Make it deployable (new service) | Deploy pipeline and a rollback that is exercised | Infra | A documented rollback is not a rollback. | 23 | Y | Not started
25 | 1 — Make it deployable (new service) | Make the demo profile impossible outside local | application-demo.yml, a CI assertion | It mounts an unauthenticated SQL console and fixture data. It already refuses to start beside a real datasource; that guard must be tested, not trusted. | 12 | N | Not started
26 | 1 — Make it deployable (new service) | Decide what happens to /console and /demo in production | console/*, demo/* | They are demonstration surfaces. Remove from the production build, or gate behind the ops identity from step 46. | 12 | Y | Not started
27 | 2 — Make what exists correct | Fix arrived_at300_m | facts/TransportFactProvider.java — SQL, requiredColumns() | The column does not exist. MySQL 1054 kills the whole SELECT, so Transport does not degrade on real data — it stops. Flip inferred to confirmed in the same edit. | 1 | N | Not started
28 | 2 — Make what exists correct | Fix order_type | facts/ProductDeliveryFactProvider.java — SQL, requiredColumns() | Same failure mode. Express detection cannot work until it is right. | 1 | N | Not started
29 | 2 — Make what exists correct | Apply the paise-vs-rupees answer | dmn/transport-not-received-decision.dmn rule t2, facts/TransportFactProvider.amountFor() | No UAT order exceeds 30000. If the column is rupees, the Rs300 cap compares against a number 100x too large and can never fire. | 1 | Y | Not started
30 | 2 — Make what exists correct | Read the cancellation status from the right column | facts/TransportFactProvider.cancellationOf() | It maps from unassign_status_code; the statuses live on order_status_code. Unblocks transport rules 5a, 6 and 7. | 2 | Y | Not started
31 | 2 — Make what exists correct | Wire the job lat/long | facts/TransportFactProvider.beyondRadius(), shared/GeoService.java | Path 3 distance returns null today, so rules 8 and 9 are dead. The job location is on cs_address, not tbl_order. | 1 | Y | Not started
32 | 2 — Make what exists correct | Implement the wallet-to-PayU link | facts/RechargeFactProvider.java, shared/DuplicateCreditGuard.java | alreadyCredited for Recharge. A wrong 'not credited' pays twice. | 1 | Y | Not started
33 | 2 — Make what exists correct | Make the schema probe fail the deployment | facts/UatSchemaProbe.java | It logs an error today. A missing column should stop a release, not decorate a log. | 27, 28 | N | Not started
34 | 2 — Make what exists correct | Run the probe against the production schema | Nothing; read-only | UAT and production drift. Confirm before, not after. | 33 | N | Not started
35 | 2 — Make what exists correct | Re-run the acceptance suite and count reachable rules | tools/demo-run.sh, DemoScenarioRunTest | The exit criterion is every rule reachable through the API for the in-scope concerns. | 27-32 | N | Not started
36 | 3 — The reference slice: Recharge, end to end | Agree the Definition of Done for a production concern | docs/DEFINITION-OF-DONE.md | Write it once, before the first concern, so 'done' is not renegotiated per concern. The 'Definition of done' tab is the proposal. | — | Y | Not started
37 | 3 — The reference slice: Recharge, end to end | Replace the mock PayU gateway | payu/MockPayUGateway.java behind the existing interface; a real implementation beside it | Recharge is the ONLY concern whose money path is complete — AUTO_CREDIT_WALLET is the single registered action. That makes it the natural first slice. | 32 | Y | Not started
38 | 3 — The reference slice: Recharge, end to end | Prove idempotency against the real gateway's semantics | action/WalletCreditService.java, safety/TicketActionRecorder.java | The guard was proved against a mock. Real gateways differ in what they return on a repeat. | 37 | Y | Not started
39 | 3 — The reference slice: Recharge, end to end | Implement the reversible window | safety/TicketAction.java, a new state; V-next migration | NFR-07. Today an auto-credit is immediate and final. This introduces a state the system does not have: paid, but not yet final. | 8, 14 | Y | Not started
40 | 3 — The reference slice: Recharge, end to end | Finaliser and reversal path | New scheduled component; action/ layer | Something has to close the window, and something has to reverse inside it. | 39 | Y | Not started
41 | 3 — The reference slice: Recharge, end to end | Partner wording for money in the window | process/ResponseTemplates.java | 'Credited' and 'credited, reversible until tomorrow' are different sentences. | 39 | Y | Not started
42 | 3 — The reference slice: Recharge, end to end | Reconciliation covers Recharge | reconcile/ReconciliationService.java; scheduling | NFR-06 targets 100%. The silent case — the gateway paid and we have no row — is the reason it exists. | 37 | Y | Not started
43 | 3 — The reference slice: Recharge, end to end | Metrics for Recharge | Micrometer counters at the decision and action layers | An automation rate nobody can compute is not a target. | 54 | N | Not started
44 | 3 — The reference slice: Recharge, end to end | Runbook: Recharge | docs/runbooks/ | What to do when the gateway is down, when a credit is stuck pending, how to switch it off. | 39 | N | Not started
45 | 3 — The reference slice: Recharge, end to end | GATE — Recharge meets the Definition of Done | — | The first concern proves the definition is achievable. Every later concern is a repeat of this shape. | 36-44 | Y | Not started
46 | 4 — Production safety | Authentication and authorisation | api/*, a security config | The POC API is open. The partner app, the agent surface and the ops surface are three callers with three different rights. | 10 | Y | Not started
47 | 4 — Production safety | Rate limiting on partner endpoints | Gateway or filter | — | 46 | N | Not started
48 | 4 — Production safety | Togglz console behind real identity | safety/TogglzConsoleAuthFilter.java or an ops API | HTTP Basic with a constant-time compare is a POC-grade answer for the control that stops the bot paying people. | 46 | Y | Not started
49 | 4 — Production safety | PII position | Logging config, escalation_context, conversation_message | Partner free text and full transcripts are stored. Decide what is logged, what is kept, and for how long. | — | Y | Not started
50 | 4 — Production safety | Data retention and archival | ACT_HI_* tables, conversation_message | Flowable history gains a row per step per conversation, forever. Decide before the first slow query, not after. | 50 | Y | Not started
51 | 4 — Production safety | Finance sign-off on the audit trail | safety/TicketAction.java fields | NFR-05: every action logged with SP id, timestamp and outcome. Confirm it satisfies finance as written. | 42 | Y | Not started
52 | 4 — Production safety | Reconciliation scheduled and paging | reconcile/, alerting | An unrecorded payment — gateway paid, no row — must wake somebody. | 42 | Y | Not started
53 | 4 — Production safety | Kill switches verified per environment | safety/BotinFeature.java, Togglz state in prod | Off must mean 'do not automate', not 'fail'. | 12 | N | Not started
54 | 5 — Operability | Elastic APM and correlation ids | Dockerfile agent, MDC through delegates | The platform already runs APM. Carry one id from the partner request through the process instance to the action row. | 11 | N | Not started
55 | 5 — Operability | Health and readiness that tell the truth | actuator config | 'Up' and 'able to read the source database' are different questions. | 22 | N | Not started
56 | 5 — Operability | KPI metrics, matching the PRD | Micrometer | Automation rate, agent-connect rate, settlement accuracy, CSAT, and per-concern tier distribution. | 54 | N | Not started
57 | 5 — Operability | Alerts that mean money is wrong | Alerting config | Reconciliation mismatch; an action attempted with no outcome; a kill switch off beyond a threshold; escalation rate moving sharply on one concern. | 52, 56 | Y | Not started
58 | 5 — Operability | Structured logging | Logging config | The POC logs generously. Production needs it parseable. | 54 | N | Not started
59 | 5 — Operability | Durable decision trace | console/DecisionTrace.java | A 200-entry in-memory ring, lost on restart, is not production observability for a concern that moves money. Facts are already durable in ACT_HI_VARINST; rule outcomes are not. | 14 | Y | Not started
60 | 5 — Operability | Runbooks for the standing failures | docs/runbooks/ | Source database unreachable; gateway down; a concern escalating everything; how to turn a concern off. | 44 | N | Not started
61 | 5 — Operability | On-call ownership | — | This service moves money with no human in the loop. | — | Y | Not started
62 | 6 — Replicate the slice | Build the transport credit service | action/ — a new ActionService for AUTO_CREDIT_TRANSPORT and AUTO_CREDIT_DISTANCE | ActionRegistry holds only AUTO_CREDIT_WALLET, so Transport decides T2 correctly and then escalates. Until this exists it is a well-tested way of creating tickets. | 45 | Y | Not started
63 | 6 — Replicate the slice | Transport to the Definition of Done | facts/, dmn/, action/, reconcile/, runbook | 5,615/month, the highest-volume concern in the build. | 62, 27-31 | Y | Not started
64 | 6 — Replicate the slice | Forget MPIN to the Definition of Done | forget-mpin process, runbook | The only Tier 0/1 concern already built, and the whole of PRD Phase 1 that exists today. | 45 | N | Not started
65 | 6 — Replicate the slice | Product delay to the Definition of Done | facts/ProductDeliveryFactProvider.java | Held by the taxonomy decision: this concern has no L1 path in the PRD. | 9, 28 | Y | Not started
66 | 6 — Replicate the slice | Free-text triage: decide the classifier | classifier-service/, classifier/HttpClassifierClient.java | Still unmeasured — no key, no labelled real messages. The spec, prompt and scoring harness exist. | 45 | Y | Not started
67 | 6 — Replicate the slice | Each further in-scope concern, one slice at a time | Per concern: catalogue row, fact provider, .dmn, action if T2, tests, runbook | A concern that reads, decides, acts and is observable is shippable. A layer is not. | 45 | Y | Not started
68 | 7 — The front door (NFR-01) | Seed the full reconciled catalogue | db/migration; concern_catalogue | Help must fully replace Call Expert Care and the Ticket menu AT LAUNCH. Every concern must be reachable, even the ones the bot will not handle until Phase 3. | 9 | Y | Not started
69 | 7 — The front door (NFR-01) | Every non-automated concern reaches an agent with context | process/EscalationContextDelegate.java (built); everything after it is not | The context row already works. The handover does not exist. | 68 | N | Not started
70 | 7 — The front door (NFR-01) | Agent 2 queue and tooling | External surface + agent/AgentController.java | The POC exposes REST endpoints. Agents need something to work in. | 69 | Y | Not started
71 | 7 — The front door (NFR-01) | Outbound dialer and CTI screen-pop | External integration | NFR-04: the partner must never re-explain the issue. | 70 | Y | Not started
72 | 7 — The front door (NFR-01) | Order dropdown, top-5 bookings | New fact/step before fetchFacts; BPMN change | R-01. Every booking-specific concern depends on it. | 68 | Y | Not started
73 | 7 — The front door (NFR-01) | Audio-note L1 selection | New capability; likely the classifier | NFR-08, Hindi/Hinglish. Does not exist in any form. | 66 | Y | Not started
74 | 7 — The front door (NFR-01) | Medal bands and P1-P4 priorities | escalation_context.medal_band, routing | PRD Section 8. medalBand is currently absent — in no table this service can read. | 70 | Y | Not started
75 | 7 — The front door (NFR-01) | Agent-connect triggers C, D and E | process/PreFlightDelegate.java, a shared trigger table | B is built. D needs a shared table rather than a column per concern, or the concerns nobody remembers to add will silently never fire it. | 68 | Y | Not started
76 | 8 — Launch | Shadow mode | Log what the bot would decide beside what the agent did | The cheapest way to find a wrong mapping before it pays anyone. No user-facing change, and the strongest argument available at the go/no-go. | 45 | Y | Not started
77 | 8 — Launch | Compare shadow results per concern and set the go list | — | Switch on the concerns where the bot and the agents agree. Hold the rest. | 76 | Y | Not started
78 | 8 — Launch | Load test to expected volume | — | 59,171 tickets a month is the sheet's June figure. | — | N | Not started
79 | 8 — Launch | Rollback drill | — | Exercised on the real pipeline, with a real deployed version. | 24 | N | Not started
80 | 8 — Launch | Go / no-go against the PRD KPIs | docs/ | Automation rate, agent-connect rate, settlement accuracy, CSAT. | 77 | Y | Not started

## Summary
Phase | Steps | Done | In progress | Blocked | Not started | Discuss first | Complete
0 — Settle (no production code) | 9 | 0 | 0 | 0 | 9 | 6 | 0%
1 — Make it deployable (new service) | 17 | 0 | 0 | 0 | 17 | 7 | 0%
2 — Make what exists correct | 9 | 0 | 0 | 0 | 9 | 4 | 0%
3 — The reference slice: Recharge, end to end | 10 | 0 | 0 | 0 | 10 | 8 | 0%
4 — Production safety | 8 | 0 | 0 | 0 | 8 | 6 | 0%
5 — Operability | 8 | 0 | 0 | 0 | 8 | 3 | 0%
6 — Replicate the slice | 6 | 0 | 0 | 0 | 6 | 5 | 0%
7 — The front door (NFR-01) | 8 | 0 | 0 | 0 | 8 | 7 | 0%
8 — Launch | 5 | 0 | 0 | 0 | 5 | 3 | 0%
TOTAL | 80 | 0 | 0 | 0 | 80 | 49 | 0%
Phases 1 and 2 need no decision from anyone and can start immediately. Phase 7 is sized by other teams and should be tracked from the start even though it lands last.

## Definition of done
Definition of Done — a production concern
Proposal for step 36. Agreed ONCE, before the first concern, so that "done" is not renegotiated per concern. A concern that misses any line is not done — it is demoable.
# | Criterion | How it is checked
1 | Every column it reads exists and is marked confirmed | UatSchemaProbe passes against the production schema, and the deployment fails if it does not
2 | Every rule in its table is reachable, or documented as to why not | The acceptance run fires them; docs/SIGNAL-REGISTER.md records any that cannot
3 | If it is T2, something can actually perform the action | ActionRegistry.canPerform() returns true — otherwise it decides correctly and escalates
4 | Money moves inside the reversible window, not before it | ticket_action carries a pending state; a finaliser closes it; a reversal path exists
5 | Idempotent against the real gateway, not the mock | A repeat raise returns "already credited" and moves nothing
6 | Its kill switch works in the deployed environment | Flip it; the next request routes to a human with no restart
7 | Reconciliation covers it, both directions | Including the silent case: the gateway paid and we have no row
8 | Metrics emit for it | Tier split, automation rate, action outcomes — per concern, not in aggregate
9 | Alerts exist for its failure modes | At minimum: reconciliation mismatch, and an action attempted with no outcome recorded
10 | It has a runbook entry | What to do when its source is down, when its action fails, how to switch it off
11 | It survives the acceptance run | DemoScenarioRunTest is green on every mvn test
12 | Its escalation carries context | The agent opens computed facts, not a transcript — the partner never re-explains

## Gates
Gate | What must be true | What it unblocks | Status
G1 — the data is known | Probes 2 and 3 run; the five answers recorded | Phase 2 in full. Transport and Recharge cannot be correct without them | Not met
G2 — the taxonomy is frozen | The 8 reconciliation decisions taken; the catalogue migration written | Every concern after the reference slice. 18,087 monthly cases in Product Issues and Violations have no agreed home until this is closed | Not met
G3 — the service deploys | Image builds, config per environment, secrets from Secrets Manager, rollback exercised | Anything reaching a real partner | Not met
G4 — money is safe on MySQL | Transaction boundaries, duplicate guard and commit ordering re-proved on the real engine | Any T2 concern in production | Not met
G5 — the reference slice is done | Recharge meets every line of the Definition of Done | Phase 6. Until one concern is genuinely done, "done" is a guess | Not met
G6 — the front door exists | Every concern reachable through Help; agent handoff works end to end | Launch. NFR-01 allows no parallel legacy entry point | Not met
G7 — shadow agrees | Bot decisions compared against agent actions, per concern | Switching concerns on. This is the evidence the go/no-go rests on | Not met